## Slide 1: RRAT – Dredging Update
Gilbert Island Post Construction
Flex Pipe Update
Flex Pipe use
2014 Dredging Update
Dredge Master Plan

## Slide 2: Gilbert Island, Mile 298 UMR
  Recent Dredging History 2005 – 2010
    Total 510k CY, Average 101k CY, Average 7 days
  Chevrons constructed 2011
  No Dredging after construction
  Estimated savings $300k to $500k.

## Slide 3: Flex Pipe - Update
+ Completed Thomas N. George Spill Barge
+ Quick Connect Demo, & in use.
Need 6 more quick connects.
Need swivel ball joint at spill barge
Off season storage
Notes: Dredge Potter and new Thomas N. George spill barge showing fixed point placement with a dustpan dredge.

## Slide 4: Flex Pipe - Use
+ Mel Price Pool – all 7 dredging locations (221, 227, 229, 235, 237, 240, 241)
+ Lower River
  Planned at mile 173
  Possibly mile 24 & other assignments until cold weather
  Buffalo Island mile 25 – 26
+ Lower River 2013
  Manskers, 104 – 103 UMR, 11-26 Sep 2013
    100k into Chevron at 104, 200k into Island
Notes: Dredge Potter and new Thomas N. George spill barge showing fixed point placement with a dustpan dredge.

## Slide 5: Dredge Potter Flex Pipe Fixed Point Placement
Allows Potter to reach preferred placement areas.
Avoid sensitive habitat areas
Create islands vs sidecasting
Notes: Dredge Potter and new Thomas N. George spill barge showing fixed point placement with a dustpan dredge.

## Slide 6: 2014 Dredge Update
Dredge Potter
  Mel Price Pool, 1 Aug 2014 – 27 Aug, 854k CY.
    7 locations: 221, 227, 229, 235, 237, 240, 241.
  Pool 25. 27 Aug – 1 Sep. 222k CY.
    Miles 252, 256, 270
  Lower River (Open River)
    1 location complete, mile 169.
    High water delays.
Dredge Bill Holman (LRL Contract)
    SEMO Port, 3 – 6 September, 64k CY.
    Kaskaskia Mouth, 7 – 13 September, 109k CY.
Dredge Goetz (St. Paul District)
    Illinois Waterway, 26 Sept to approx 13 Oct, (mile 79 – 75)
2013 Quantities: Potter 6.6M CY, America 1.5M CY

## Slide 7: 2014 Dredge Update
  High Water delays, only 1 assignment completed to date, mile 169 UMR, on Lower River
  Schedule Impacts (Only 1 location complted to date)

## Slide 8: Dredge Master Plans
+ July 31st Meeting with USFW, MDOC, IDNR
+ Documented preferred placement for routine dredging areas.
+ Identified dredging areas for flex pipe use.
Need to finalize, working on template..
ILW Master Plan.